## Sheet1
Wideband Delphi Estimation
Project: Rent A Car |  | Estimation Unit: Hours
Estimation Team Member: Ariba |  | Date: 22/4/22
Task | Initial Estimate | Change 1 | Change 2 | Final
Requirement Gathering | 4 | 0 |  | 4
Develop requirements document | 6 | -2 |  | 4
HTML Design and Creation | 6 | 4 |  | 10
Stand Alone Component | 3 | 3 |  | 6
Database Implementation | 3 | -1 |  | 2
Middleware Development | 2 | -1 |  | 1
Graphics and Interface | 6 | 3 |  | 9
Content Creation | 1 | 1 |  | 2
Testing And Production | 3 | 2 |  | 5
Net Change |  | 9
Total | 34 | 43 |  | 43
Wideband Delphi Estimation
Project: Rent A Car |  | Estimation Unit: Hours
Estimation Team Member: Anjiya |  | Date: 22/4/22
Task | Initial Estimate | Change 1 | Change 2 | Final
Requirement Gathering | 5 | -1 |  | 4 |  | Ariba | Anjiya
Develop requirements document | 4 | -1 |  | 3 | Initial Estimation | 34 | 43
HTML Design and Creation | 8 | 2 |  | 10 | Delta 1 | 43 | 44
Stand Alone Component | 5 | 1 |  | 6
Database Implementation | 5 | -2 |  | 3
Middleware Development | 3 | -1 |  | 2
Graphics and Interface | 6 | 3 |  | 9
Content Creation | 3 | -1 |  | 2
Testing And Production | 4 | 1 |  | 5
Net Change |  | 1
Total | 43 | 44 |  | 44
Wideband Delphi Estimation
[5 empty] | Project: Rent A Car |  | Estimation Unit: Hours
[5 empty] | Task | Ariba | Anjiya | Best Case | Worst Case | Averge Case
[5 empty] | Requirement Gathering | 4 | 4 | 4 | 4 | 4
[5 empty] | Develop requirements document | 4 | 3 | 3 | 4 | 3.5
[5 empty] | HTML Design and Creation | 10 | 10 | 10 | 10 | 10
[5 empty] | Stand Alone Component | 6 | 6 | 6 | 6 | 6
[5 empty] | Database Implementation | 2 | 3 | 2 | 3 | 2.5
[5 empty] | Middleware Development | 1 | 2 | 1 | 2 | 1.5
[5 empty] | Graphics and Interface | 9 | 9 | 9 | 9 | 9
[5 empty] | Content Creation | 2 | 2 | 2 | 2 | 2
[5 empty] | Testing And Production | 5 | 5 | 5 | 5 | 5
[5 empty] | Total | 43 | 44 | 42 | 45 | 43.5